## Sheet1
Task | Start Date | End Date | Duration
Brainstorm Ideas | 2017-09-27 | 2017-09-29 | 2
Develop UX/UI Prototypes | 2017-09-28 | 2017-10-01 | 3
Write Overview of Project | 2017-09-29 | 2017-10-01 | 2
Define Group Breakdown | 2017-09-29 | 2017-10-01 | 2
Construct Scheduling Chart | 2017-09-29 | 2017-10-01 | 2
Develop Mapping Code & Database Relation | 2017-09-29 | 2017-10-02 | 3
Construct Databases - 1) User 2) File DB 3) User Saved File DB | 2017-09-29 | 2017-10-02 | 3
Build Working UI: - Login (password functionality not required for this step | 2017-09-29 | 2017-10-02 | 3
Build Working UI: - Safety Tracker | 2017-09-29 | 2017-10-03 | 4
Get User Login Working | 2017-10-02 | 2017-10-05 | 3
Preliminary Integratation of Front End and Back End | 2017-10-03 | 2017-10-05 | 2
Build Working UI: - Weather Map | 2017-10-03 | 2017-10-05 | 2
Build Working UI: - Article/Blog Entry | 2017-10-04 | 2017-10-05 | 1
Full Integration of Front and Back End | 2017-10-05 | 2017-10-07 | 2
Project Polishing: ReadMe for project | 2017-10-07 | 2017-10-09 | 2
Project Polishing: Write-up of future features | 2017-10-07 | 2017-10-09 | 2
Project Polishing: Write-up of several how-to guides | 2017-10-07 | 2017-10-09 | 2
Final Deployment to Heroku | 2017-10-08 | 2017-10-09 | 1